Course risk management plan

| Course: | Terlinag Rd |
| --- | --- |

| Risk point: | Start point on Terlinga Rd at start of event |
| --- | --- |
| Risk description: | Traffic heading east on Terlinga Rd, or turning east off Black Heath Rd, colliding with riders at the start |
| Proposed action: | Signage for traffic on Terlinga Rd and Black Heath Rd for traffic approaching the start point |
| Personnel requirements | No additional requirements: starter sets riders off when clear to do so |

| Risk point: | Turnaround points at the northern and western ends of Terlinag Rd |
| --- | --- |
| Risk description: | Cars approaching the turnaround points from both directions colliding with riders taking the u-turn |
| Proposed action: | Signage and marshals to slow and stop traffic in both directions at each u-turn point. |
| Personnel requirements | Marshals x 4- 2 at each u-turn point Marshal instructions: - Stop or slow traffic when riders approaching. - Call to riders when clear |

| Risk point: | Finish line |
| --- | --- |
| Risk description: | Riders crossing the white line at the finish. Riders congregating at the finish line blocking traffic Timers and finish line officials safety for passing traffic |
| Proposed action: | Notification to warn and slow traffic north and eastern side of the finish line on Terlinga road. For larger bunch finishes, option to stop traffic both east and west of the finish line until riders are clear. Commissaire briefing to riders – if traffic is not stopped, riders must not cross the white line. Commissaire briefing to riders, and finish line officials, to instruct riders to clear the finish area. |
| Personnel requirements | - Marshals (up to 2) if traffic is to be stopped at the finish - Finish line official to ensure riders and spectators keep clear of the road at the finish. |