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Course management plan

	Course:
	Corkscrew Hill Climb



	Risk point:
	Start point – riders moving onto Corkscrew Road and starting their ride.

	Risk description:
	Traffic heading north and south on Corkscrew Rd colliding with riders as the start

	Proposed action:
	Signage to slow and stop traffic approaching the start point.
Marshal to stop car approaching from the south

	Personnel requirements
	Marshals x1 – on Corkscrew Rd (on the southern side of Sixth Creek bridge).
Marshall instructions
· Stop traffic when riders starting



	Risk point:
	Intersection of Corkscrew Rd and Montacute Rd

	Risk description:
	Traffic heading east on Montacute Rd colliding with riders turning left off Corkscrew Rd
Vehicles turning right off Montacute Rd onto Corkscrew Rd, cutting the corner, and colliding with riders turning left off Corkscrew Rd

	Proposed action:
	Signage to slow and stop traffic approaching the intersection heading east on Montacute Rd
‘Event ahead’ signage for vehicles approaching the intersection from the south on Montacute Rd plus safety cones on Corkscrew Rd at the intersection to direct cars to not cut the corner if turning right,
Marshal to stop cars approaching from the west along Montacute Rd

	Personnel requirements
	Marshals x1 – on Montacute Rd: Marshall instructions
· Stop traffic when riders approaching to take the left-turn.
Spotter x 1 – Corkscrew Rd: Spotter instructions
· Signal the marshal when riders are approaching the intersection



	Risk point:
	Finish line

	Risk description:
	Riders congregating at the finish line blocking traffic
Timers and finish line officials safety for passing traffic

	Proposed action:
	Signage to warn and slow traffic north and south of the finish line on Marble Hill Road.
Commissaire briefing to riders, and finish line officials, to instruct riders to clear the finish area.

	Personnel requirements
	Finish line official to ensure riders and spectators keep clear of the road at the finish.
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